## Project Plan
[Note: to choose a different table layout, click in the table, select the Design menu ribbon and choose a table style]
GDPR Preparation Project Plan
NOTE: All tasks and resources are approximations and will depend on the specifics of your project.
Ref. | Task | Effort (man-days) | Resource | Start Date | End Date
1 | GDPR review and initial training and advice |  | Top Management,Legal,External Training Provider
2 | Project initiation |  | Project Manager
3 | Establish document control |  | Information Security Manager,Project Manager
4 | Define roles, responsibilities and authorities |  | Information Security Manager,Top Management
5 | Appoint Data Protection Officer |  | Top Management
6 | Identify lead Data Protection Supervisory Authority |  | Data Protection Officer,Top Management,Legal
7 | Document communications procedures |  | Business Representatives,Project Manager,Data Protection Officer
8 | Competence and training needs assessment |  | Business Representatives,Project Manager,Data Protection Officer
9 | GDPR-related training and familiarisation |  | Business Representatives,Data Protection Officer,Information Security Manager,Internal Audit Team,Top Management,IT Management
10 | Audit of personal data |  | Data Protection Officer
11 | Identify lawful basis for processing personal data |  | Data Protection Officer,Legal
12 | Define personal data retention and protection policy |  | Data Protection Officer,Business Representatives,Information Security Manager
13 | Define information security policies |  | Information Security Manager,Top Management,Data Protection Officer
14 | GDPR and information security awareness training |  | Business Representatives,Data Protection Officer
15 | Create or amend privacy notices |  | Data Protection Officer
16 | Review and amend consent methods and procedures |  | Data Protection Officer,Business Representatives,IT Management
17 | Age-related consent and controls (children) |  | Data Protection Officer,Business Representatives,IT Management
18 | Agreements for international transfers of personal data |  | Data Protection Officer,Business Representatives,Legal
19 | Create and implement subject request procedures |  | Data Protection Officer,Business Representatives,IT Management
20 | Define data protection impact assessment process |  | Data Protection Officer,Business Representatives,IT Management
21 | Data protection impact assessment training |  | Data Protection Officer,External Training Provider,Business Representatives,IT Management,Information Security Manager
22 | Create information security incident management procedure |  | Data Protection Officer,Information Security Manager,Business Representatives,Legal
23 | Create personal data breach notification procedure |  | Data Protection Officer,Top Management,Business Representatives,IT Management
24 | Information security incident management training |  | Data Protection Officer,Information Security Manager,Business Representatives,Top Management
25 | Test incident management procedure |  | Data Protection Officer,Information Security Manager,Business Representatives,Top Management
26 | Post Project Review |  | Project Manager,Information Security Manager,Top Management,Business Representatives,Data Protection Officer,Legal
27 | GDPR becomes law